## Slide 1
European Clearing House for Open Robotics Development Plus Plus
Monitoring procedures and platform
Reinhard Lafrenz
TUM
Experiment Kick-Off Paris, January 15th, 2015

## Slide 2
What is the monitoring for?
To ensure that all experiments are on track
To identify potential problems and their causes
To support the experiments in case of problems, delays, etc.
To guide the experiments towards impact creation
To have a global overview of the status of all experiments
To prepare the formal periodic reports

## Slide 3
Roles in the monitoring process
Experimenters:
Provide information about the progress of the experiments
Ideally more multi-media based (videos, photos, simulations, …) than text
Discuss the state with their moderator
Moderators:
Assignment of two moderators individually to each experiment
Familiarity with the application field and/or the methods/technology
At least one of them also familiar with the administrative issues and procedures to support the experiment

## Slide 4
Monitoring Procedure:
Month 2
Month 4
Month 6
…
Monitoring periods: after every two months
Components of the monitoring
Images, Videos, Simulations, etc.
Report
Short (!) explanatory text
Self- assessment
Traffic Lights
Moderator assessment
Problems, delays, any other info
Blog discussion
Support by moderator

## Slide 5
Writing the reports (1)
Edit
Add comment
Experiment’s self-assessment
Moderator’s assessment

## Slide 6
Writing the reports (2)

## Slide 7
Financial Issues
Budget Management Tool on the ECHORD++ Online Portal
Connected to Financial Tool!

## Slide 8
Moderator assignment for the experiments

## Slide 9
Thank you.
Questions?
The ECHORD Plus Plus Consortium acknowledges support by the European Commission under FP7 contract 601116.