## Project
Name of the project | LA-ROSES
Date of evaluation | 2017-01-04
Name of the external expert (s) | Prof. Andreas Müller
Name of the internal expert (s) | Dr. Hardik Shah, Dr. Yannick Morel
Experiment participants
Place of evaluation | Pisa, Italy

## Goals and outcomes
Proposed outcome(s) of the project
#1
#2
Proposed goal(s) of the project
#1
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
#1. Cycle time |  |  | Slightly slower than humans, but good enough and meeting target.
#2. Minimize the material losse (unnecessary removal of cheese) Start The human worker in the current process., End material loss 0.5‐1% of total weight smaller than with manual work |  |  | It is there, but requires more data to be acccurately quantified.
#3. Development of 3D sensor set‐up with 1D laser distance sensors |  |  | Done.
#4. Start Existing passive and active force control techniques, End prototype of 1 DO passive force control system with adjustable force setpoint Month 6, D1.2 (Milestone 1) |  |  | Did not include force sensing, slowed down control loop. Major deviation, but very well motivated.
#5. Integration of 3D sensing and force control |  |  | Same comment as above.
#6. Implementation of software architecture for constraint‐based trajectory generation and motion control Start - Results of 5) |  |  | OK.
#7. Start The human worker in the current process, End Automated system with on‐the‐fly 3D surface measurement and trajectory adaptation Month 18 Milestone 3 37 |  |  | Details are not there, but final demonstrator is functional.
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
#1. Direct labour cost saving in comparison to manual work |  |  | Discussion of this should include the necessity to turn the cheese block over to shave all 6 surfaces.
#2. Cheese loss reduction |  |  | Need to be better shown/quantified. But customers seem convinced.
#3. Selling Price |  |  | Business case has been made in agreement with customers.
#4. Scalability to other manufacturing operations (deburring, grinding, polishing) and transfer to other industrial branches outside food industry. |  |  | It is there, but has not been very actively investigated.
Milestones
Number | Delays | Evaluation | Comments
#1. Early system integration |  |  | I have no problem believing it.
#2. System Operational |  |  | Same as above.
#3. Experiment show-case |  |  | Final prototype working well, expected higher TRL honestly, lots of moving pieces and human intervention.
Deliverables
Number | Delays | Evaluation | Comments
RIF. Report on RIF visit outcome |  |  | Did not use a RIF because they had no use for it, which is fine.
D 1.1. Revised experiment specification and planning |  |  | No particular problem.
D 1.2 Early integration (demonstration of laser sensing and force control implementations) |  |  | The deliverable only provides a very short description of the implementation, no actual demonstration. Also discusses software architecture.
D 1.3 Experimental system & algorithm description |  |  | Control parameters are mentioned, but no detail on the concrete control algorithm used is provided.
D 2.1 Software Architecture |  |  | Only superficial overview of the architecture is provided, which is overall fine. More problematic is the discussion of the manner in which delays are treated, which lacks details and is confusing. Discussion of trajectory generation is similarly lacking.
D 3.1 Final demonstration |  |  | Questions regarding the performance metric, how was the loss of cheese (claimed 3 to 4%) measured? Also, how do you do the sides and bottom? Latter point has been raised since proposal review. NB: cheese loss number different in final report (there: claims 4.5 to 5%). Concerns partly cleared during final review.
SB Story Board |  |  | The storyboard provides a project outline, not the expected MMR storyboard, but that is OK.
MMR |  |  | MMR provides a link to a video of the working prototype. Not ideal for two reasons: 1) having a video directly would have been more convenient (as is, we're hostage of how long the video will be hosted), 2) presentation of the projects's broader achievements (beyond only a prototype demo) would have been appreciated.
Dissemination activities
Number | Delays | Evaluation | Comments
#1. Fairs (e.g. Automatica, vision & robotics, MNE Trade fair, Hannover Messe, Industrial European Dairy Show)
#2. Experiment Website |  |  | Expected later.
#3. Journal publication (e.g. Robotics and Automation Magazine, Journal of Dairy Science) |  |  | Expected later.
#4. Conference (e.g. International Symposium on Robotics (ISR)) 13 |  |  | Expected later.
#5. Media coverage (e.g. De Tijd, Trends Magazine) |  |  | FDR working under NDA, unable to perform it, which is fine.
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
0
Commercial activities |  |  | In contact with 2 possible customers.
Project plan (task) execution |  |  | No problem.
Deviation/mitigation management |  |  | Moved away from force sensing, for good reasons.
Overall progress of the project |  |  | Expected a higher final TRL than achieved.
Budget usage according to the proposal |  |  | No major issue detected.
Sincerity and commitment of the partners |  |  | Very good contact with Experimenters.
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?