## Project
Name of the project | LA-ROSES
Date of evaluation | 2017-01-04
Name of the external expert (s) | Prof. Andreas Müller
Name of the internal expert (s) | Dr. Hardik Shah, Dr. Yannick Morel
Experiment participants
Place of evaluation | Pisa, Italy

## Goals and outcomes
Proposed outcome(s) of the project
#1
#2
Proposed goal(s) of the project
#1
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
#1. Speed up in development/ programming/ setup |  |  | Practical, qualitative testing suggests this is achieveable, not tested on the originally targeted HW.
#2. Number of trajectory key points |  |  | As above, tests suggest it is achievable, not clearly quantitified however.
#3. Quality of the trajectory |  |  | Unclear whether an improvement can be expected.
#4. Speed up in execution |  |  | As for #1., tests suggests the method has the potential, not tested on target HW nor quantified.
#5. Scalability of the learning algorithm for different platforms |  |  | There are no questions that the approach does indeed scale easily. Issues (requiring significant efforts) can be expected in its implementation on (old) HW however.
#6. Human robot interaction strategie |  |  | Demonstrated through implementation.
#7. Safety consideration for certification purposes |  |  | Unclear. Experimenters claim safety considerations at CLOOS are limited to joint angle limits and joint angle velocities. In which case the approach can be made to satisfy such criteria.
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
#1. Impact on Cloos: reduction of development costs by estimated up to 25% |  |  | On iKPIs 1 to 5, work performed, if used by CLOOS, could tend to provide such benefits. However, that would be on a significantly longer term than that of the present project. Factually, none of these iKPIs are achieved as of present. However, CLOOS has expressed an interest in pursuing the work undertaken in the project.
#2. Impact on Cloos: Reduction of production costs for end consumer
#3. Impact on Cloos: programming will be made easier - less application support from Cloos will be necessary
#4. Impact on Cloos: secure and possibly increase market share. Support work places in Europe
#5. Competitors
#6. Scalability (general) New, for Cloos non-competitive applications can potentially be reached by reusing the functionality |  |  | Scalability and generalizability to other applications are clear and well established.
#7. Scalability (general) The methods to be developed could be used in other applications and domains
#8. Scalability (general): The methods to be developed can also be used on only mildly redundant robots |  |  | Tested previously.
Milestones
Number | Delays | Evaluation | Comments
#1. Requirements and TRL levels available
#2. Working proof-of-concept in simulation
#3. Working prototype in real-world scenario |  |  | Not implemented on the targeted system, algorithm still implemented and tested on an actual (simpler) system, at the industrial partner's.
Deliverables
Number | Delays | Evaluation | Comments
#1. Requirements for reference application |  |  | Document provides a broad, qualitative overview of the targeted application(s). It does not provide detailed requirements.
#2. Simulation of high-DOF welding robot teaching
#3. Video: Teaching redundancy resolutions and welding tasks in simulation using shared human-machine control
#4. Design of user study in real-world welding tasks |  |  | Document essentially empty. Difficulties with the industrial partner made it so that it was not possible to carry the user study.
#5. Story Board
#6. Multi-Media Report
Dissemination activities
Number | Delays | Evaluation | Comments
#1. CLOOS customer information newsletter |  |  | Limited involvement of the industrial partner.
#2. Fair |  |  | Unable to work out the logistical details due to unavailability of resources on the industrial partner's side.
#3. Press coverage
#4. Conferences |  |  | Submitted.
#5. Video |  |  | Multimedia report video prepared.
#6. Demonstration Bielefeld Transfer Lab |  |  | A number of demonstrations took place in the Bielefeld lab.
#7. Concertation Meetings |  |  | Participation in ERF and ECHORD++ workhops.
#8. Robotics workshop |  |  | Workshop intended to be organised with production technology association.
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
Commercial activities |  |  | N/A
Project plan (task) execution |  |  | Pursued objectives and executed reasonably well in spite of major difficulties, see below.
Deviation/mitigation management |  |  | Change of personnel at industrial partner created problems, leading to lack of commitable resources from CLOOS. Academic partner pursued efforts nonetheless, and managed to achieved reasonable results in spite of challenges.
Overall progress of the project |  |  | Objectives not fully achieved, but reasonable progress given circumstances.
Budget usage according to the proposal |  |  | OK as far as I can tell, CLOOS expected to reduce cost claims in line with reduced committed resources.
Sincerity and commitment of the partners |  |  | Sincerity and commitment of academic partner: good. Commitment of industrial partner was not sufficient to allocate the expected ressources for a more satisfactory project completion.
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?