## Project
Name of the project | DEBUR
Date of evaluation | 2017-01-19
Name of the external expert (s) | Jordi Palacín
Name of the internal expert (s) | Antoni Grau
Experiment participants | Fundación Tekniker, IDELT
Place of evaluation | Fundación Tekniker, Eibar, Spain

## Goals and outcomes
Proposed outcome(s) of the project
#1 | Cost reduction up to 20% per part for the deburring operation
#2 | Volume of new lubricants and abrasives reduced by 30%
#3 | Reduction of scrap parts by 30%
#4 | Lower protrusion and smoother surface
Proposed goal(s) of the project
#1 | The goal of the experiment was to design and set up an automated robotic station prototype for laser deburring of metal casting 3D parts
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
tKPI #1 | in time |  | OK
tKPI #2 | in time |  | Deviation respect the original proposal
tKPI #3 | in time |  | OK
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1 | in time |  | not verified
iKPI #1 | in time |  | not verified
iKPI #1 | in time |  | deviated
iKPI #1 | in time |  | OK
iKPI #1 | in time |  | OK
iKPI #1 | in time |  | not verified
Dissemination activities
Number | Delays | Evaluation | Comments
#1 | in time |  | OK
#2 | in time |  | OK
#3 | in time |  | OK
#4 | in time |  | Not achieved
#5 | in time |  | OK
#6 | in time |  | OK
#7 | in time |  | Not achieved
#8 | in time |  | Not achieved
#9 | in time |  | OK
#10 | in time |  | OK
Milestones
Number | Delays | Evaluation | Comments
MS #1 | in time |  | OK
MS #2 | in time |  | OK
MS #3 | in time |  | OK
Deliverables
Number | Delays | Evaluation | Comments
SB | DELAYED 3 WEEKS
MMR | DELAYED 6 WEEKS
RIF | DELAYED 4 MONTHS |  | The contact with RIF was difficult
D1.1 | DELAYED 2 MONTHS
D2.1 | DELAYED 4 WEEKS
D2.2 | DELAYED 3 WEEKS
D3.1 | DELAYED 1 WEEKS
D4.1 | DELAYED 4 WEEKS
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
|  |  | 0 | Remaining
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?