## Project
Name of the project | Dexbuddy
Date of evaluation | 2016/07/29
Name of the external expert (s) | Patrick van der Smagt
Name of the internal expert (s) | Fabio Bonsignorio
Experiment participants | ArtiMind and KIT: in presence; Shadow and AEA: partly remotely
Place of evaluation | Karlsruhe

## Goals and outcomes
Proposed outcome(s) of the project
#1 | integration of the available robot, new hand, and camera systems (completed)
#2 | integration of the ArtiMinds intuitive programming software suite (completed)
#3 | application specification (partly completed)
#4 | evaluation and benchmarking (partly completed)
#5 | dissemination (not completed) and exploitation (promising: a less technically ambitious application is developed in an innovation project with Siemens AG)
Proposed goal(s) of the project
#1 | developing of a demonstrator of an easily programmable dexterous robotic co-worker for real industrial scenarios
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
tKPI #1 |  |  |  |  | all “not ok” in the portal. But it might be the the moderators didn't pay attention to this section?
TKPI #2
TKPI #3 |  | no info | the final demo is only engineered for a specific example. So, even if no info is explicit in the report, I would put red
TKPI #4 |  | no info | the final demo is only engineered for a specific example. So, even if no info is explicit in the report, I would put red
TKPI #5
TKPI #6 |  | no info | the final demo is only engineered for a specific example. So, even if no info is explicit in the report, I would put red
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1
IKPI #2 |  |  | new project with Siemens
IKPI #3
IKPI #4 |  |  | new project with Siemens
Milestones
Number | Delays | Evaluation | Comments
MS #1
MS #2
MS #3
MS #4
MS #5
Deliverables
Number | Delays | Evaluation | Comments
SB
MMR
RIF
1.1 MMR Hardware | 5 months |  | acceptable
2.1 Report Software | 12 months
3.1 | 6 monts |  | acceptable
4.1 | - |  | ok
5.1
Dissemination
Number | Delays | Evaluation | Comments
1
2
3
4
5
6
7 |  |  | video (really??? I don't think it was on public display)
8
9
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
|  |  | 0 | Remaining
Comments: | Figures not available. Important remarks: less hardware bought than in the proposal, less travels than in the proposal, some orginal PM very generous compared to the work. It is expected that not the full budget is claimed!
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners |  |  |  | if not red!
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?