## Project
Name of the project | LA-ROSES
Date of evaluation | 2017-01-04
Name of the external expert (s) | Prof. Andreas Müller
Name of the internal expert (s) | Dr. Hardik Shah, Dr. Yannick Morel
Experiment participants
Place of evaluation | Pisa, Italy

## Goals and outcomes
Proposed outcome(s) of the project
#1
#2
Proposed goal(s) of the project
#1
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
#1. DOF identification |  |  | There are no significant concerns over tKPIs of the project. The technical work proposed originally was conducted in a serious, reasonable way. Some reservations could be expressed over some of the finer scientific points (e.g. regarding the specifics of the algortihmic control architecture), but those concerns remain minor, and the final prototype works well enough in practice, up to the standards necessary for clinical trials for acceptability.
#2. Improved kinematics for children
#3. 3D mobility; Start: ATLAS setup + (1) + (2), End: Improved prototype
#4. Adjustable size of patients between 4-8 years children
#5. Sensor integration
#6. Gait control
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
#1. Providing the ability to walk |  |  | Arguable, although technically correct. The patient is able, using the equipment, to locomote using something similar to a walking gait. Which is a feat in itself, but the KPI label is misleading. Specifically: no, the patient is not able to gain the ability to walk, not in the sense that a healthy subject is able to walk; that is, using walking as a useful locomotion modality. The "walking" is here intended as a physical exercise or therapy. It is very positive, but the KPI label oversells things quite a bit.
#2. Acceptable time required to don and doff, and adjust from one patient to another |  |  | Other iKPIs were assessed in acceptability clinical trials. The results appear convincing. If they were good enough for clinical physicians, they are good enough for ECHORD++.
#3. Tolerance using the exoskeleton
#4. Acceptable degree of fatigue after a 10min walk
#5. Acceptable inspiratory/expiratory muscle strength IPM/EPM and/or SNIP (depending on patient age)
Milestones
Number | Delays | Evaluation | Comments
#1. Agreement on requirements and specifications for EXOTrainer 1 |  |  | No significant reservations on most Milestones.
#2. EXOTrainer concept approved 1-3
#3. Orthotics complements, mechanical upgrade and sensor system integrated
#4. Joint motion control and intention detection |  |  | Yellow here for the form (could have been a green). Motion control strategy appears a bit heuristic, usefulness of intention detection unclear (patients can not exert force with their legs, can not signify intention).
#5. Prototype ready for clinical tests
Deliverables
Number | Delays | Evaluation | Comments
D1.1 Exoskeleton requirements and specifications |  |  | Specifications are neither very detailed, nor clearly motivated or substantiated by a solid, quantified analysis.
D3.1 Progress report 3 |  |  | Fine.
D4.1 Technical Improvements to the exoskeleton |  |  | Not a terribly detailed description but good enough to appreciate changes from ATLAS to EXOTrainer.
D4.2 Exoskeleton for SMA gait training |  |  | Don't know what was precisely expected, but the deliverable is a single spec sheet of the previous prototype, ATLAS, does not match my expectations.
D4.3 Exoskeleton for gait training: User Guide |  |  | A little shallow, does not appear to provide sufficient details to possible users.
D5.1 report on clinical evaluation outcome |  |  | Detailed and official. Unfortunately in Spanish.
SB Storyboard |  |  | No actual MMR storyboard, but that is a minor problem. They provide a very nice cartoon overview of the project.
MMR |  |  | Some solid videos.
Dissemination activities
Number | Delays | Evaluation | Comments
#1. Experiment website |  |  | Solid website for an e++ Experiment.
#2. Social media |  |  | verified presence on youtube, although mainly through their MARSI Bionics channel.
#3. Trade Fairs |  |  | They have had a presence in a number of fairs, they are attending innorobo in 05/17 (which is after their final review).
#4. Journal publications |  |  | Only one verified such publication, in a low profile journal.
#5. Conferences |  |  | Reasonable but not great. No ICRA or IROS. Some CLAWAR.
#6. Coverage in specialized press |  |  | Seems reasonable.
#7. MMR |  |  | Well polished video.
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
0
Commercial activities |  |  | Difficult to assess as there are no first sales yet, product still pursuing its CE marking. But, well established demand for the product. The business plan lacks a sound, quantified analysis, but there are no doubts the consortium is serious about bringing the product to market. They have associated themselves with a third party who will provide the means necessary for initial small-scale series production.
Project plan (task) execution |  |  | No problem whatsoever.
Deviation/mitigation management |  |  | No significant ones, delays (in clinical trials) due to some E++ delays out of their control.
Overall progress of the project |  |  | Outstanding, high-TRL final product (EC TRL scale: TRL8, qualified product; medical TRL scale: TRL6).
Budget usage according to the proposal |  |  | No significant concerns detected.
Sincerity and commitment of the partners |  |  | Sincerity and commitment are unquestionable.
Experiments needing extension
Is the exension required due to unforeseen circumstances? |  |  | NA
Deviation requested? Is the alteration/mitigation plan satisfactory? |  |  | NA
Does the project plan in the extended period help in achieving the original/deviated goals? |  |  | NA
Should the project be extended as demanded? |  |  | NA