## Project
Name of the project | ECHORD++ GAROTICS
Date of evaluation | 5 DECEMBER, 2016
Name of the external expert (s) | FRANCISCO ROVIRA-MÁS
Name of the internal expert (s) | FRANCESCO MAURELLI
Experiment participants | STRAUSS, UNIVERSITY OF BREMEN
Place of evaluation | BUXTEHUDE, GERMANY

## Goals and outcomes
Proposed outcome(s) of the project
#1 | Enhance the asparagus detection rate as well as the harvesting rate. Detection success higher than 95 %.
#2 | Develop a new gripping mechanism with three robotic arms.
#3 | Collect data to forecast yield and plan next harvest runs.
#4 | Achieve a harvesting capacity of up to 1,000 asparagus stalks per hour.
Proposed goal(s) of the project
#1 | Develop and implement technological improvements to the green asparagus harvesting robot built under the AmLight project.
#2 | Full automatic harvesting of green asparagus with only one operator for 2-3 machines.
#3 | Increase the European competiveness in asparagus production by creating new and healthier working places.

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
tKPI #1 | ok |  | The increase of the detection rate for individual stalks has improved with the 3D analysis of point clouds.
tKPI #2 | ok |  | Harvesting performance is fine in terms of speed but second gripping behavior needs improvement.
tKPI #3 | ok |  | The sorting of asparagus stalks into two quality categories was successfully implemented.
tKPI #4 | ok |  | The third harvesting arm was not implemented as the performance of the second arm still needs to improve.
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1 | Ok |  | STRAUSS believes that the machine can be sold for 100 k€. This is, according to CWS, an acceptable price but still seems a bit too high for me. I would target a reduction of 30 % - 50 %.
iKPI #2 | Ok |  | As there is no automatic harvesting system available on the market, the potential is huge for manufacturing and selling the harvester. Together with CWS, who also wants to distribute the machine in the UK market, STRAUSS has developed a business plan after the successful field tests.
iKPI #3 | Ok |  | The prototype has reached TRL 7. The fine technical step is to scale the existing prototype up to become a 3-dam harvester pulled by a tractor.
Milestones
Number | Delays | Evaluation | Comments
MS #1 | OK |  | There are some videos available in the website.
MS #2 | ? |  | Flyers, posters and roll-ups are supposed to be ready, although I did not see them during the external review.
MS #3 | OK |  | The corresponding RIF-deliverable was uploaded to the ECHORD platform on 4 November 2015.
MS #4 | Ok |  | The GARotics experiment has been presented at two exhibitions, the AUTOMATICA in Munich (2016) and at ITROS in Hamburg (2015).
MS #5 | Ok |  | In total 8 communication / dissemination activities have been performed. A detailed report can be found as deliverable MMR.
MS #6 | Ok |  | The website is linked to the AmLight website (www.amlight.eu) as the GARotics page
Deliverables
Number | Delays | Evaluation | Comments
D 1.1 |  |  | Implementation report. The system is described although the algorithms are not explained.
D3.1 |  |  | Field experiment report of first season. A video was available.
D3.2 |  |  | Field experiment report of second season. No quantitative evaluation was carried out.
RIF |  |  | Report on RIF visit. The report seems to be too short and images would have helped to understand the experiences narrated.
MMR |  |  | Multi-Media Report. Good dissemination.
SB |  |  | Story board for video. It is strange that the deliverable is the story board rather than the finished video (set as a milestone).
D4.10 |  |  | The GARotics exploitation plan lacks the key information to understand how the machine price is established, the benefits and turnover for each partner, and the selling strategy.
Dissemination activities
Number | Delays | Evaluation | Comments
1 video
2 flyers
3 RIF visit |  |  | not really much dissemination with RIF
4 Exhibitions
5 Press Coverage |  |  | not too much general press coverage
6 website
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
|  |  | 0 | Remaining
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?