## Project
Name of the project | LA-ROSES
Date of evaluation | 2017-01-04
Name of the external expert (s) | Prof. Andreas Müller
Name of the internal expert (s) | Dr. Hardik Shah, Dr. Yannick Morel
Experiment participants
Place of evaluation | Pisa, Italy

## Goals and outcomes
Proposed outcome(s) of the project
#1
#2
Proposed goal(s) of the project
#1
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
#1. The development of the end effector (equipped with force feedback and distance sensor) |  |  | There was a deviation based on the requirements. It was agreed and the new design works.
#2. The development of the mechatronic handpiece (Sensor integration to fix the distance of the fiber tip of the diode laser) |  |  | There was a deviation in the cocept. The new system works according to the required functionlity.
#3. Image guided surgery |  |  | Does not full fill the requirements. Recognition of the cut was not accurate, repeatable and robust.
#4. Accuracy of the positioning for the integrated system with robot arm and end effector |  |  | No quantifiable meausres are provided. Robot is not able to bring the system in position reliably.
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
#1. Scalability: Application in different eye surgery operations (a universal joint to be connected at a generic robotic arm) |  |  | It could be applied to other eye surgeries, however, no concrete substanciation provided. Only a single statement.
#2. Creation of new spin-off (one) with five people (one person at the end of the experiment and an additional 4 after one year) |  |  | Not planned
#3. Certification / CE marking |  |  | Not planned
Milestones
Number | Delays | Evaluation | Comments
#1. System architecutre |  |  | A concept is provided. Details are lacking.
#2. End of design and dev phase |  |  | Yes it ended.
#3. End of test phase |  |  | There was no evidence of a proper testing. Neither a concept for test is provided.
#4. End of project |  |  | Yes it ended.
Deliverables
Number | Delays | Evaluation | Comments
RIF. Report on RIF visit outcome |  |  | They interacted with some RIF people. However, no clear details provided.
D 1.1. Report on management organisation
D 2.1 Surgical Method & System Architecture
D 3.1 Designing of eye handpiece
D 3.2 Control unit and consolle SW scheme |  |  | Mainly contains publicaly available information.
D 3.3 Eye hand-piece first version release
D 3.4 Test report |  |  | No test data provided.
D 4.1 Vision system development |  |  | Documentation is OK, however, implementationw as not good.
D 1.2 Intermediate report on project activities |  |  | Not submitted in the light of final report.
D 5.1 Robotic platform design specification and development
D 6.1 First release of integrated robotic platform |  |  | some documentation provided however system does not work as required.
D 6.2 Preliminary tests report |  |  | Does nto qualify as a test report.
D 7.2 Test report on eye model |  |  | Although not completely self contained.
D 7.3 Histological test report
D 7.4 Eye hand-piece final version release |  |  | Cad models provided
D 7.5 Final release of integrated robotic platform |  |  | Comparable to D6.1, only minor additions. Only PPT, no real platform provided.
SB Story Board
MMR |  |  | MMR and SB are not following
D 1.3 Final report on project activities |  |  | No substantial results.
D 7.6 Final Test report |  |  | No test pattern, no test concept, simple copy paste from previous reports.
D 8.1 Dissemination, Exploitation & Training report |  |  | Some dissemination evidences. However, most of the contents not useful.
Check if the dissemination acknoledges the project or not.
Dissemination activities
Number | Delays | Evaluation | Comments
#1. First press release |  |  | Unable to track or verify KPI.
#2. Second press release |  |  | Unable to track or verify KPI.
#3. Third press release |  |  | Unable to track or verify KPI.
#4. Twitter, facebook, website |  |  | Unable to track or verify KPI.
#10. RO-MAN 2016, IEEE International Symposium on Robot and Human Communication |  |  | Unable to track or verify KPI.
#12. MEDICA |  |  | Unable to track or verify KPI.
#13. Press contacts to: Autonomous Robot, Transactions on Biomedical Engineering, Transactions of Neural Systems & Rehabilitation Engineering, Journal of Rehabilitation Medicine, Medical Device Development, European Medical Device Technology, Medical Device an |  |  | Some dissemination efforts were performed, in particular a publication in a video journal. However, intially targeted journal publications were not verifiably achieved.
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
0
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?