## Project
Name of the project | LINARM
Date of evaluation | December 16 2016
Name of the external expert (s) | Eugenio Guglielmelli
Name of the internal expert (s) | Simona Crea
Experiment participants | CNR, UL and Idrogenet Teams
Place of evaluation | Milano ITIA CNR

## Goals and outcomes
Proposed outcome(s) of the project
#1 | extremely affordable and portable device for upper limb robot-mediated neurorehabilitation
#2 | the device should be able to adapt rehabilitation parameters to the actual needs of each patient
#3 | the device should enable to achieve longer and more effective rehabilitation sessions by increasing patient’s engagement
Proposed goal(s) of the project
#1 | An easily wearable FES (Functional Electrical Stimulation)
#2 | An engaging on-line adaptable rehabilitation scenario and virtual environment
#3 | Sensory system for measuring patient’s physical activity and physiological state
#4 | A patient model for adapting training task parameters
#5 | A central control system able to constantly update rehabilitation parameters with the aim of ful- filling the needs of the patient.

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
tKPI #1 | 0
2 | 0
3 | 0
4 | 0
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1 | 0
2 | 0 |  | Production costs exceed 3000 Euro
3 | 0
4 | 0
5 | 0? |  | Clinical validation with patients not performed
Dissemination activities
Number | Delays | Evaluation | Comments
#1 | 0
2 | 0
3 | 0
4 | N/A |  | self-assessment
5 | N/A |  | self-assessment
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
Milestones
Number | Delays | Evaluation | Comments
MS #1 | 0
2 | 0
3 | 0
4 | 0
Deliverables
Number | Delays | Evaluation | Comments
SB | 0
MMR | 0
RIF | 0
D1.1 | 0
D1.2 | 0 |  | A clear exploitation path is not identified, more R&D will be needed to attract industrial investment
D1.3 | 0
D2.1 | 0
D2.2 | 0
D3.1 | 0
D3.2 | 0
D4.1 | 0 |  | Full proof of concept of the mechatronic solution and of the integrated system is not available
D4.2 | 0 |  | Patient verification is missing
D5.1 | 0
D5.2 | 0
D5.3 | 0
Resource usage table
Item | Budget received | Consumed | Available |  | NOTE: Data about the Resource Usage refer to what was reported in the Final Report.
Personal | NA | 223331.65 | #VALUE!
Travel | NA | 11783.27 | #VALUE!
Equipment | NA | 1579 | #VALUE!
Consumable | NA | 31623.8 | #VALUE!
| 297320 | 396427.16 | #VALUE! | Remaining
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?