## Project
Name of the project | MOTORE++
Date of evaluation | 14/15.09.2016
Name of the external expert (s) | Prof. Paolo Fiorini
Name of the internal expert (s) | Dr. Hardik Shah
Experiment participants
Place of evaluation | Pisa, Italy

## Goals and outcomes
Proposed outcome(s) of the project
#1 | A precise robot for upper limb training.
#2 | wireless commnication with the PC
#3 | Number of games to practice.
Proposed goal(s) of the project
#1 | Create a robot which helps stroke patients in rehabilitation to speed up the recovery.
#2 | A portable robot for remote rehabilitation
#3

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
tKPI #1
tKPI #2 |  |  | For future work more formal usability test.
tKPI #3
tKPI #4 |  |  | How much effort is it to add more exercises? Maybe provide an environment for therapysts to design their own games. Ensure plug and play of new games into the existing system
tKPI #5
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1 |  |  | Provide a proof of cost reduction
iKPI #2
iKPI #3
iKPI #4
Milestones
Number | Delays | Evaluation | Comments
M1 | 2 months |  | give yelloe lights in the due month. Make green afterwards
M2 | 2 months |  | give yelloe lights in the due month. Make green afterwards
Dissemination activities
Number | Delays | Evaluation | Comments
#1 1st press release
#2 2nd press release |  |  | Will be released after the end of the project
#3 3rd press release
#4 website, twitter, facebook |  |  | Due later
#5 Paper submission: 1st MMVR / IFCARS Joint Conference on Human Machine Interface | Delayed |  | Further clinical trials required for appropriate dissemination
#6 Paper submission: ICVR, International Conference On Virtual Rehabilitation | Delayed |  | Further clinical trials required for appropriate dissemination
#7 Paper submission: ICORR, International Conference On Rehabilitation Robotics | Delayed |  | Further clinical trials required for appropriate dissemination
#8 Paper submission: EMBC, 37th Annual International Conference Of The Ieee Engineering In Medicine And Biology Society | Delayed |  | Further clinical trials required for appropriate dissemination
#9 Paper submission: ICRA 2106, IEEE International Conference on Robotics and Automation |  |  | Substituted by other reputed conferences
#10 Paper submission: RO-MAN 2016, IEEE International Symposium on Robot and Human Communication |  |  | Substituted by other reputed conferences
#11 Paper submission: EMBC, 38th Annual International Conference Of The Ieee Engineering In Medicine And Biology Society | Delayed |  | Further clinical trials required for appropriate dissemination
#12 MEDICA 2015 |  |  | Substituted by other reputed conferences
#13 Press contacts to: Autonomous Robot, Transactions on Biomedical Engineering, Transactions of Neural Systems & Rehabilitation Engineering, Journal of Rehabilitation Medicine, Medical Device Development, European Medical Device Technology, Medical Device and Diagnostic Industry, Medizin&Technik
Deliverables
Number | Delays | Evaluation | Comments
TR1
TR2
D1.1
D2.1
D2.2 | Delayed by 2 months |  | Due to supplier problems. Overall goals are still reached hence, green light.
RIF | Delayed by 2 months
D3.1 | Delayed by 2 months
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
|  |  | 0 | Remaining
Commercial activities
Project plan (task) execution
Deviation/mitigation management
Overall progress of the project
Budget usage according to the proposal
Sincerity and commitment of the partners
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?