## Project
Name of the project | pickit
Date of evaluation | 2016-11-18
Name of the external expert (s) | Rui Loureiro
Name of the internal expert (s) | Fabio Bonsignorio
Experiment participants | Veit Mueller, Felix Penzlin, Norbert Elkmann (IFF)
Place of evaluation | Madgeburg(Germany) Fraunhofer IFF premises

## Goals and outcomes
Proposed outcome(s) of the project
#1
#2
Proposed goal(s) of the project
#1
#2

## Evaluation
Please insert your evaluation of the project in the traffic light format
Technological progress (technical KPIs)
Number | Delays | Evaluation | Comments
All KPIs |  |  | Excellent and timely
socio-economical progress (impact KPIs)
Number | Delays | Evaluation | Comments
iKPI #1 | Dealyed by x months
NA |  |  | Well commented and achieved
Dissemination activities
Number | Delays | Evaluation | Comments
All planned | timely |  | Exceeding expectations
Milestones
Number | Delays | Evaluation | Comments
All mes | Timely |  | Excellent
Deliverables
Number | Delays | Evaluation | Comments
All D | timely |  | Excellent
Resource usage table
Item | Budget received | Consumed | Available
Personal |  |  | 0
Travel |  |  | 0
Equipment |  |  | 0
Consumable |  |  | 0
|  |  | 0 | Remaining
Commercial activities |  |  | Ok
Project plan (task) execution |  |  | Ok
Deviation/mitigation management |  |  | Ok
Overall progress of the project |  |  | Ok
Budget usage according to the proposal |  |  | Ok
Sincerity and commitment of the partners |  |  | Ok
Experiments needing extension
Is the exension required due to unforeseen circumstances?
Deviation requested? Is the alteration/mitigation plan satisfactory?
Does the project plan in the extended period help in achieving the original/deviated goals?
Should the project be extended as demanded?